|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **2010-2011** – Consideration Phase - Application for candidate status due 4/1/11  | **2011-2012** – Candidate Year I – 12 month duration | **2012-2013** – Candidate Year 2: 12 months | **2013-2014** – Candidate Year 3: 12 months |
| **Roxboro & Fairfax – PYP Primary Years Programme****Roxboro M MYP**Note: Fairfax & Rox M will follow same sequence beginning 2011-12Est Budget: Application fees-Required PDPD costs should be less in 2012 when KSU becomes an approved training center | Professional Development:Fall 2010: * Tara, Stacy S, Joe to initial training
* Ordered IB PYP Starter Packs
* Site visits for Rox Teachers scheduled 1/11-3/11: Oberlin and Bexley schools
* First staff training, (5 core teachers and Tara3/11 Alb NM

Identify IB Coordinator; post position Feb 11; available for training April 1* ½ time Rox E coord
* ½ time facilitator for Fairfax/Rox M application process
* 2011-12 becomes .50 Rox E and .50 Rox M Coord.

Prepare plan to have all staff complete initial category I workshop by 8/11By April, 2011: Complete & submit Application A & \*Application Fee - $9,500 per building annual fee until authorization; $7,300 thereafter annuallyCollaborative Planning: Those attending PD (above) begin developing units with grade level; during 2011-12 planning time to be adjusted with time during Chinese instruction.* 1 unit will be developed prior to 2011-12

Problem of Inquiry PlanningSummer after majority of staff have attending training1-2 days (indistrict) | Professional Development:* Work with IB-appointed consultant for onsite 2 day visit & 20 remote hours

Continue sending staff to workshops (Categories 1-3) or schedule August Category 1 workshop for all staffCollaborative Planning: Continue systems of collaborative planning through Chinese language release time to develop units of inquiry* + 1 additional unit developed per semester

Planning: School programming must consider design for transdisciplinary units (i.e., eliminates departmentalization); determine G/T service model; Intervention design within units  | Professional Development:* Continue remote work with IB-appointed consultant
* Continue attending workshops (Categories 1-3), documenting evidence of participation so that proof of 100% staff attending official PYP workshop by authorization

Complete alignment to IB Requirements:* Programme of inquiry
* Units of inquiry
* School assessment policy
* School language policy

Collaborative Planning: Continue systems of collaborative planning through Chinese language release time to develop units of inquiry* Complete required unit development
 | Professional Development:* Continue attending workshops (Categories 1-3)

Prepare application part BPrepare for IB On-Site Visit - * All staff must have attended an official IB PYP workshop (regional or school)
* The school must have completed and documented six units of inquiry per grade level that have been planned, written, and reflected upon

**Winter 2014 Roxboro Elementary officially designated as Roxboro World School by IB International followed by Fairfax and Roxboro Middle School in 2015.** |